## Trauma Registry Attachment B
APPENDIX A - TRAUMA REGISTRY REQUIREMENTS
PROJECT EXPERIENCE |  | EXPLANATION
Number of years as an Trauma Registry vendor, if applicable
Number of state run Trauma Registry implementations, if applicable
Number of new state run Trauma Registry implementations over the last 3 years
SCOPE OF WORK SPECIFICATIONS | YES, INCLUDED | YES, ADDITIONAL COST | NO | EXPLANATION
PROJECT MANAGEMENT
Designated Account Manager for the life of the contract whose role is to ensure business requirements are being fulfilled and be an excalation point for questions and support.
Designated Project Manager to coordinate and schedule implementation, configuration and associated deliverables.
Bidder must provide a general project schedule of each major phase to include timeline, data migration from current vendor, implementation, configuation, testing and training. General project schedule must be attached to bidder response. |  | Verify timeline is either in narrative or Scope.
Upon contract award, bidder must provide a detailed project schedule that must include, at a minimum:
Business analysis
Establish test and production environments
System setup
System configuation
Data migration and configuration
Testing and acceptance
Training and assistance
GENERAL SYSTEM REQUIREMENTS
Bidder must provide software to comply with the National Trauma Data Bank (NTDB) and the Kentucky Trauma Registry Data Dictionary (KTRDD) and continue to meet future NTDB and KTRDD standards going forward at no additional cost to CHFS.
Identify a comprehensive list of hardware and software needed by users at CHFS and facilities to allow access and use of the system.
Bidder must provide a solution that is web-based and hosted by the bidder who will be responsible for the database and technical infrastructure.
Allow data collection, analysis and reporting by authorized users via a web-based application using:
Desktops
Laptops
Tablets
iPad
Smart phones
System(s) should be capable of functioning on common browsers.
Operate efficiently with all Internet connections including broadband, wireless and mobile connections.
Allow an unlimited number of users.
The Trauma Registry system must be scalable.
Bidder will supply a live and test environment of the proposed software solution.
TRAUMA REGISTRY FUNCTIONALITY
The system shall allow for the customization of workflows.
Allow for users to select from lists of pre-determined answers allowed by NTDB, KTRDD or CHFS. Sort order of lists should be controlled by CHFS system administrators.
Allow the CHFS system administrators to control validation, e.g. ability to make a data element required for the entire system.
Questions that have validation must visually highlight the respective answer field.
Bidder's software should provide a score or other indicator of data completeness
The system should calculate field values whenever possible, e.g., age, Glasgow Coma Score and Revised Trauma Score.
Allow for the development of template forms by CHFS for customized workflow and mandated questions.
Software should support facilities' ability to create facility defined questions unique to the facility or use additional questions included in the software.
Bidder has template forms available for CHFS system administrator modification.
Users have the ability to save and exit a partial record without completing the record and return to finish at a later time.
Past records can be easily retrieved for review and modifcation. Search parameters must be customizable.
System should auto save patient records periodically.
Users with multiple facility affiliations can use a single user ID and password and select the relevant facility affiliation. Users can have different security or access levels at each facility.
Allow facilities to search and retrieve or import patient pre-hospital and referring hospital information from the CHFS Trauma Registry and/or CHFS EMS PCR systems.
Allow for facilities to retrieve or import multiple EMS agencies' PCRs for each patient.
Allow for the upload of supplemental documentation such as pictures, pdf, word, etc.
SECURITY, SECURITY FEATURES, AND CONFIDENTIALITY
Trauma Registry must be securely accessed via internet connection.
Trauma Registry must prevent unauthorized access to the system.
Allow an unlimited number of end user permission groups.
CHFS shall have full administrative rights and access over all system(s) functions.
Meet or exceed Health Insurance Portability and Accountability Act (HIPAA). Bidder will explain how information is stored and the security to protect PHI.
Must include procedures for safeguarding the system from unauthorized modifications. | cost proposal for license, charge or any supplement software licensing costs.
Bidder shall provide an audit trail for all submissions, access, print, create, read, update, and delete operations performed on submitted data records including user name and date/time. These reports should be compliant with all HIPAA requirements.
Bidder shall describe the end user security protocols including password protocol, end users ability to reset lost or expired passwords, automatic log off procedures, and administrators ability to lockout user(s). |  |  |  | NEED IT TO PUT IN WHAT SYSTEM SECURITY AND TESTING TO ADHERE TO IF ANY AND ADD TO THIS SECTION. Data segregation if server is shared or do we want own server or do we self host (Don't think this is preferred). What about bidder will not copy our data unless approved, secure connections for data transmission.
Describe how the product meets HITECH, and other security requirements.
Provide secure system hosting, maintenance and support.
Data is to be housed on servers that are:
Physically secure with procedures for control of security.
Backed up on servers in a minimum of two (2) different locations.
Provide detailed responses for the process, procedure and communication plan to prevent data loss, disaster recovery of data, or security breaches.
Operational 99.8% of the calendar year. Quarterly reports are to be provided that identify operational status during the previous quarter and the process to notify end users the system will be down for planned or unplanned maintenance.
Process for security audits.
Bidder will describe the process they will use to report to CHFS any unauthorized access to or security incidents where data may have been compromised within 24 hours.
Ability to adjust or modify facility tree structure, if applicable, to meet business needs of CHFS.
SYSTEM ADMINISTRATION
Have an integrated data validation tool/module to ensure data submitted is accurate and valid.
System should provide an announcement feature or similar functionality so CHFS system administrators can announce system changes.
IMPORT AND EXPORT REQUIREMENTS
Allow the CHFS and authorized users to export data to other data systems in the following formats to include, but not limited to:
i. XML
ii. Microsoft® (MS) Access®
iii. Microsoft SQL export file requirements
a) bcp export file of only Kentucky data
b) The corresponding bcp format file
c) Command line file which calls bcp import to import the exported bcp file into the CHFS database.
iv. HL7 Standard where applicable.
v. FHIR
Provide monthly backups of the database accessible to the CHFS for download with the following Microsoft SQL export file requirements:
i. bcp export file of only Kentucky data
ii. The corresponding bcp format file
iii. Command line file which calls bcp import to import the exported bcp file into the CHFS database.
Must have interface options to allow data exchange to and from other NEMSIS and NTDB compliant systems.
Bidder's software will provide real time validation against national and state schematron rules upon import. Validation should reject record(s) from being imported into the CHFS system upon failure to meet Schematron rules. Messages must be reviewable by facilities importing or exporting data.
Extensible Markup Language (XML) compliant with NTDB.
Must have interface options to allow data exchange to and from other NEMSIS and NTDB compliant systems.
NTDB submission module able to export all required NTDB elements to the national trauma registry.
Provide an importing interface for receiving data from other trauma registries and software products.
REPORTING
Provide a data analysis engine or a report generator that will provide standard (no customization) reports, ad hoc custom reporting and:
The ability to analyze data.
Allows approved users to generate statistical information from the aggregate patient care data through an Internet based query tool.
Allows for dynamic and customized analysis without additional programming by the bidder.
Creates charts with identifying labels and appropriate scientific units.
Provides the ability to export reports into PDF®, Excel® and Word® formats.
Provide the ability to schedule reports with various time intervals and with changing parameters.
Specific Data Analysis requirements:
Provide the user the ability to apply simple mathematical formulas across data element. For example, researchers need to be able to take two independent data codes and create a new data field that will contain the sum, difference, average, product, mean, median or quotient of the NTDB and NTRDD data fields.
All data fields in the query and analysis section are to be labeled with their appropriate NTDB data code. The Trauma Registry should have hover help or some other means of identifying which NTDB data code is being collected. This will allow researchers to easily evaluate and find the proper data codes even if the data fields have been renamed for familiarity.
Provide CHFS a live or near live data repository to be used for reporting. A data dictionary, how data is linked in tables, what the data elements are in each table, and other relevant documentation must be provided.
Provide CHFS with the ability to import data into other CHFS systems.
TRAINING
Provide train-the-trainer instruction and materials, webinar-based training for users and on-line user manuals for instruction on use of the application with information on data elements that are current and reflect all updates.
Provide on-site implementation training.
Provide post go live training.
EMS PCR DATA INTERFACE (for future consideration)
The system will interface with receiving facilities to appropriately receive EMS PCR information through data upload (preferred) or print capability.
Interface allows for the linkage of patient outcome data from the facility and EMS agency.
SERVICE, SUPPORT AND ENHANCEMENTS REQUIREMENTS
Provide an assigned account manager for the Kentucky implementation.
Provide a system help file available to all users.
Provide help desk support for CHFS staff available during normal business hours. Describe what support options are available (e.g. phone, chat, support ticket, etc.).
Support must be available 24x7x365 for critical system failures or issues.
Provide the process or procedures for response times for all levels of support, escalation process of support, support tracking system, and support severity level determinations.
Provide new versions released only after they have been fully tested and found to be error free and at a time mutually agreeable with CHFS.
Provide for timely system fixes and resolution of issues deemed critical by CHFS, applied or installed after appropriate testing by the bidder and approval of CHFS.
Have regular maintenance schedule policies, to be provided to CHFS, that explain when the system would not be available to Kentucky users.
Improve the system based on CHFS identification of weaknesses, feature enhancements, and needed adjustments and provide a timeline for completion. Provide a description on how CHFS improvements are prioritized related to other client requests.
Describe the process for the the archival, use and retrieval for data.
DATA MIGRATION REQUIREMENTS
Migrate data from the CHFS's current provider identifying the length of time needed for conversion, testing and implementation of the proposed system(s) to full operational use by CHFS and authorized users. The steps are to include:
Defining data to be imported.
Linking/mapping data to fit the new system. |  | Legacy data?
Testing results.
Importing a complete set of data.
DATA OWNERSHIP REQUIREMENT
All data collected by the system(s) will be owned exclusively by the CHFS and transferrable in a format approved by CHFS to it or its designee upon contract termination/expiration.
END OF CONTRACT REQUIREMENT
The bidder shall be responsible for end of contract activities at the completion of the contract to ensure that the transition from bidder's operations by the successor or CHFS occurs smoothly and without disruption to CHFS. End of contract transition activities will include planning, timely transfer of data and documentation specifically for Kentucky at no additional cost. This obligation survives the termination of the contract. |  | How long? What is consider timely?
What if bidder goes out of business or sells
CUSTOM PROGRAMMING
The bidder shall provide hourly pricing for any current and future custom programming needs to meet specific requirements for the Trauma Registry as requested and mutually agreed upon by the bidder and CHFS.
OPTIONAL - The following are each independent and optional only and should be included as optional in bidder's response and quote.
Provide integration solutions to state Health Information Exchange (HIE).
ADDITIONAL SOFTWARE FEATURES
Provide a detail of any additional software features not already covered and if they are included in the cost or at additional cost.
PRODUCT DESCRIPTION | QUANTITY |  |  | PRICING
HER Suite with Quality Management & Mobile - Includes Quality Management , Ad Hoc Reports, Analytics, Patient Tracker. Allows for unlimited users, unlimited mobile applications, live support, state and federal data reporting, ongoing weekly web training, software, updates, and upgrades | 11000/Incidents
CAD Integration - Allows for Integration of CAD data into HER mobile and web application. Ongoing maintenance included. Additional fees from our CAD vendor may apply. | 11000/Incidents
Cardiac Monitor - Unlimited cardiac monitors, allows for import of cardiac monitor data via local or cloud integration. Ongoing maintenance included | 11000/Incidents
Billing Standard Interface - Allows for Integration of discrete ePCR data into third-party billing software. Ongoing maintenance included. | 11000/Incidents
Invoicing for custom work
Daily Rates
Travel Expenses